## plan
id | area | title | value_json | pros | watchouts | one_way | rationale | source_url | terraform_resource | owner | status | terraform_path | deploy_status | updated_at
D-001 | infra | Region eu + CMEK | {"location": "eu", "encryption": "cmek", "cmek_config_id": "default", "kms_key": "projects/PROJECT_ID/locations/europe/keyRings/ge/cryptoKeys/gemini-enterprise"} | Meets EU data residency (GDPR) ¦ You control the keys; supports third-party connectors | Region cannot be changed after data stores exist ¦ Key cannot be swapped once applied; all connectors share one CMEK config ¦ First-party connectors use Google-managed keys (except BigQuery/GCS import) ¦ Cloud KMS billed continuously once registered | YES | Residency + key-control requirements | https://docs.cloud.google.com/gemini/enterprise/docs/cmek | google_discovery_engine_cmek_config | planning-agent | deployed | terraform_out/D-001_infra.tf | validate-failed | 2026-09-03T23:17:10Z
D-002 | app | App: "Employee Assistant" | {"app_name": "Employee Assistant", "audience": "all_employees", "capability": "search_summarize", "actions_enabled": false, "app_type": "APP_TYPE_INTRANET", "collection_id": "default_collection"} | Fastest path to broad value; one simple permission scope ¦ Read-only; lowest risk; no per-user OAuth | Cannot create tickets or send mail (add an actions app later) | no | Broad value with least privilege | https://docs.cloud.google.com/gemini/enterprise/docs/quickstart-gemini-enterprise | google_discovery_engine_search_engine | planning-agent | deployed | terraform_out/D-002_app.tf | validate-failed | 2026-09-03T23:17:10Z
D-003 | infra | Region eu + Google-managed keys | {"location": "eu", "cmek_config_id": null, "kms_key": null, "encryption": "gmek"} | Meets EU data residency (GDPR) ¦ Simplest; nothing to manage | Region cannot be changed after data stores exist ¦ You do not hold the keys; can't move THIS project to CMEK later without a rebuild | YES | Residency + key-control requirements | https://docs.cloud.google.com/gemini/enterprise/docs/cmek | (none) | planning-agent | saved |  |  | 2026-09-03T23:31:11Z
D-004 | app | App: "askInfo" | {"capability": "search_summarize", "app_type": "APP_TYPE_INTRANET", "app_name": "askInfo", "actions_enabled": false, "collection_id": "default_collection", "audience": "specific_team"} | Tight, least-privilege scope ¦ Read-only; lowest risk; no per-user OAuth | Narrower initial value; more apps as you expand ¦ Cannot create tickets or send mail (add an actions app later) | no | Scoped access suited to actions | https://docs.cloud.google.com/gemini/enterprise/docs/quickstart-gemini-enterprise | google_discovery_engine_search_engine | planning-agent | saved |  |  | 2026-09-03T23:32:42Z
D-005 | infra | Region eu + CMEK | {"location": "eu", "encryption": "cmek", "cmek_config_id": "default", "kms_key": "projects/PROJECT_ID/locations/europe/keyRings/ge/cryptoKeys/gemini-enterprise"} | Meets EU data residency (GDPR) ¦ You control the keys; supports third-party connectors | Region cannot be changed after data stores exist ¦ Key cannot be swapped once applied; all connectors share one CMEK config ¦ First-party connectors use Google-managed keys (except BigQuery/GCS import) ¦ Cloud KMS billed continuously once registered | YES | Residency + key-control requirements | https://docs.cloud.google.com/gemini/enterprise/docs/cmek | google_discovery_engine_cmek_config | planning-agent | saved |  |  | 2026-09-04T14:59:06Z